## Project_Info
Project Name | Manual Testing of nimapinfotech Website
Reference Document | https://testffc.nimapinfotech.com/
Created By | Mayuri A. Jadhav
CreatedDate | 2025-11-18
Approved Date

## Test Scenarios
Test Scenario ID | Test Scenario Description | No of Test Cases | Passed | Failed
(TS_001) Sign Up | Validate Working of Sign Up Page | 23 | 15 | 8
(TS_002) forgot Password | Validate Working of forgot Password Page | 16 | 14 | 2
(TS_003) Sign with OTP | Validate Working of Sign with OTP Page | 20 | 18 | 2
(TS_004) Login | Validate Working of Login Page | 16 | 13 | 3
Total |  | 75 | 60 | 15

## Sign Up
Test Case ID | Test Case Description | Pre Condition | Steps to Execute | Test Data | Expected Result(ER) | Actual Result | Status | Executed QA Name
TC_001 | Verify URL of nimapinfotech is working | Open any browser | 1. Enter URL of nimapinfotech in search bar 2. Press enter | URL of nimapinfotech: https://testffc.nimapinfotech.com/ | Validate URL of nimapinfotech should be working | nimapinfotech URL is working fine and visible Login page | Pass | Mayuri A. Jadhav
TC_002 | Verify user should able to click on Sign up button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1. Hover mouse pointer on Sign Up button 2. click on button | Not Applicable | 1. Arrow cursor should change to Hand Cursor 2.Sign Up button should be highlighted 3. when user click on Sign Up button user should get directed to respective page | Arrow cursor change to Hand Cursor.Sign Up button is highlighted and User is get directed to respective page | Pass | Mayuri A. Jadhav
TC_003 | Verify appropriate text on title bar of website | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.hover mouse pointer to title bar of webpage | Not Applicable | following message should get displayed: "Register-Test Field Force" | "Test Field Force" message is displayed | Fail | Mayuri A. Jadhav
TC_004 | Verify the design of the Sign Up page should be displayed properly | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.Check whether design of the Sign Up page is displayed properly | Not Applicable | design of the Sign Up page should be displayed properly | design of the Sign Up page is displayed properly as expected | Pass | Mayuri A. Jadhav
TC_005 | Verify the logo of the employee attendance tracking should be visible on Register Form | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.Check whether logo of the employee is visible on Register Form | Not Applicable | logo of the employee attendance tracking should be visible on Register Form | logo of the employee attendance tracking is visible on Register Form as expected | Pass | Mayuri A. Jadhav
TC_006 | Below of logo, Verify the Headline should be visible on Register Form | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3. Check whether Below logo Headline is visible | Not Applicable | Below logo, Headline should be visible on Register Form | Below logo, Headline is visible on Register Form as expected | Pass | Mayuri A. Jadhav
TC_007 | Verify all required fields should be marked with star | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.Check required fields are marked with star | Not Applicable | all required fields should be marked with star | As expected all required fields are marked with star | Pass | Mayuri A. Jadhav
TC_008 | Verify that user should not able to submit register form with blank Name,Country,Mobile no. and Email id field | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check if submit button is clickable with blank fields | Not Applicable | user should not able to submit register form with blank Name,Country,Mobile no. and Email id field.Highlighted error message should be shown'Required field' | User is not able to submit register form with blank fields.Error message shown. | Pass | Mayuri A. Jadhav
TC_009 | Verify in each textbox placeholder should be present | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check placeholder are present in each textbox | Not Applicable | placeholder should be present in each textbox | As expected placeholder are present in each textbox | Pass | Mayuri A. Jadhav
TC_010 | Verify user should able to fill all the fields | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether user fill all the fields | Name-Sanu Country-India Mobile No-4857485965 Email Id-sanu@gmail.com | user should able to fill all the fields | user are able to fill all the fields | Pass | Mayuri A. Jadhav
TC_011 | Verify in Name field numbers and special characters should not be allowed | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether numbers and special characters are not allowed in Name field | Name-*#$478 | In Name field numbers and special characters should not be allowed.Highlighted error message should be shown numbers and special characters are not allowed. | In Name field numbers and special characters are allowed | Fail | Mayuri A. Jadhav
TC_012 | Verify in Mobile No field character and special characters should not be allowed | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether characters and special characters are not allowed in Mobile No field | Mobile No-asd*%# | In Mobile No field numbers and special characters should not be allowed.Highlighted error message should be shown characters and special characters are not allowed. | In Mobile No field characters and special characters are not allowed but wrong error message shown'minimum field length:6' | Fail | Mayuri A. Jadhav
TC_013 | Verify in Mobile No field minimum 10 digit should be allowed | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether in Mobile No field minimum 10 digit are allowed | Mobile No-4857485965 | In Mobile No field minimum 10 digit should be allowed | In Mobile No field minimum 6 digit are allowed | Fail | Mayuri A. Jadhav
TC_014 | Verify user should not able to submit register form with invalid email id | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether register form submit with invalid email id | Email Id- abcgmail, fhg@, cvcb@gmail, wed@gmail. | user should not able to submit register form with invalid email id | As expected user is not able to submit | Pass | Mayuri A. Jadhav
TC_015 | Verify user should not able to submit register form with valid email id and other fields blank | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether register form submit with invalid email id and other fields blank | Not Applicable | user should not able to submit register form with valid email id and other fields blank | user is not able to submit register form with valid email id and other fields blank | Pass | Mayuri A. Jadhav
TC_016 | Verify that user should not able to submit register form with already used email id. | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether register form submit with already used email id. | Email Id-sanu@gmail.com | user should not able to submit register form with already used email id. | user is able to submit register form with already used email id. | Fail | Mayuri A. Jadhav
TC_017 | Verify that in country field dropdown user can able to select another countries | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether in country field dropdown user can able to select another countries | Not Applicable | country field dropdown user can able to select another countries | country field dropdown user is able to select another countries | Pass | Mayuri A. Jadhav
TC_018 | When user selecting country other than India all fields should be marked star | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether in country field dropdown user can able to select another countries | Not Applicable | When user selecting country other than India all fields should be marked star | selecting country other than India Mobile No field is not marked star | Fail | Mayuri A. Jadhav
TC_019 | Verify that user should submit register form, filling with all fields | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether register form submit, filling with all fields | Name-Sanu Country-India Mobile No-4857485965 Email Id-sanu@gmail.com | user should submit register form, filling with all fields | user is able to submit register form after filling all fields | Pass | Mayuri A. Jadhav
TC_020 | Verify user should be get successful message after submitting register form | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether user get successful message after submitting register form | Not Applicable | user should be get successful message after submitting register form | User is not getting successful message and user is redirected to reset password page | Fail | Mayuri A. Jadhav
TC_021 | Verify that user should able to click on Forgot password, Back and Submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether user click on Forgot password, Back and Submit button | Not Applicable | user should able to click on Forgot password, Back and Submit button | user is able to click on Forgot password, Back and Submit button | Pass | Mayuri A. Jadhav
TC_022 | Verify that Forgot password, Back and Submit button should be highlighted | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether Forgot password, Back and Submit button are highlighted | Not Applicable | Forgot password, Back and Submit button should be highlighted | Forgot password, Back are not highlighted, only Submit button is highlighted | Fail | Mayuri A. Jadhav
TC_023 | Verify that Arrow cursor should change to Hand Cursor on Forgot password, Back and Submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Sign Up button 3.check whether Arrow cursor change to Hand Cursor on buttons | Not Applicable | Arrow cursor should change to Hand Cursor on Forgot password, Back and Submit button | Arrow cursor is getting changed to Hand Cursor on Forgot password, Back and Submit button | Pass | Mayuri A. Jadhav

## forgot Password
Test Case ID | Test Case Description | Pre Condition | Steps to Execute | Test Data | Expected Result(ER) | Actual Result | Status | Executed QA Name
TC_001 | Verify URL of nimapinfotech is working | Open any browser | 1. Enter URL of nimapinfotech in search bar 2. Press enter | URL of nimapinfotech: https://testffc.nimapinfotech.com/ | Validate URL of nimapinfotech should be working | nimapinfotech URL is working fine and visible Login page | Pass | Mayuri A. Jadhav
TC_002 | Verify user should able to click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1. Hover mouse pointer on Forgot Password button 2. click on button | Not Applicable | 1. Arrow cursor should change to Hand Cursor 2.Forgot Password button should be highlighted 3. when user click on Forgot Password button user should get directed to respective page | Arrow cursor change to Hand Cursor.Forgot Password button is highlighted and User is get directed to respective page | Pass | Mayuri A. Jadhav
TC_003 | Verify appropriate text on title bar of website | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.hover mouse pointer to title bar of webpage | Not Applicable | following message should get displayed: "Forgot Password-Test Field Force" | "Test Field Force" message is displayed | Fail | Mayuri A. Jadhav
TC_004 | Verify the design of the Forgot Password page should be displayed properly | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.Check whether design of the Forgot Password page is displayed properly | Not Applicable | design of the Forgot Password page should be displayed properly | design of the Forgot Password page is displayed properly as expected | Pass | Mayuri A. Jadhav
TC_005 | Verify the logo of the employee attendance tracking should be visible on Forgot Password page | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.Check whether logo of the employee is visible on Forgot Password page | Not Applicable | logo of the employee attendance tracking should be visible on Forgot Password page | logo of the employee attendance tracking is visible on Forgot Password page as expected | Pass | Mayuri A. Jadhav
TC_006 | Below of logo, Verify the Headline should be visible on Forgot Password page | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3. Check whether Below logo Headline is visible | Not Applicable | Below logo, Headline should be visible on Forgot Password page | Below logo, Headline is visible on Forgot Password page as expected | Pass | Mayuri A. Jadhav
TC_007 | Verify that user should not able to click submit button with blank Email id/Mobile No. field | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check if submit button is clickable with blank fields | Not Applicable | user should not able to click submit button with blank Email id/Mobile No. field | User is not able to click submit button with blank fields.Error message shown. | Pass | Mayuri A. Jadhav
TC_008 | Verify in textbox placeholder should be present | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check placeholder are present in textbox | Not Applicable | placeholder should be present in textbox | As expected placeholder is present in textbox | Pass | Mayuri A. Jadhav
TC_009 | Verify user should able to fill the fields | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether user fill the fields | Email Id-sanu@gmail.com | user should able to fill the fields | user is able to fill the fields | Pass | Mayuri A. Jadhav
TC_010 | Verify in Email Id/Mobile No field 10 digit number should be allowed | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether in Email Id/Mobile No field 10 digit number should be allowed | Mobile No-4857485965 | Email Id/Mobile No field 10 digit number should be allowed | Email Id/Mobile No field minimum 10 digit are allowed and if mobile no exist,user is able login | Pass | Mayuri A. Jadhav
TC_011 | Verify user should not able to click on submit button with invalid email id | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether user should not able to click on submit button with invalid email id | Email Id- abcgmail, fhg@, cvcb@gmail, wed@gmail. | user should not able to click on submit button with invalid email id | As expected user is not able to click submit button | Pass | Mayuri A. Jadhav
TC_012 | Verify only registered Email Id/Mobile, users should be able to click submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether only registered Email Id/Mobile, users should be able to click submit button | Email Id-sanu@gmail.com Mobile No-4857485965 | only registered Email Id/Mobile, users should be able to click submit button | As expected only registered Email Id/Mobile, user is able to click submit button.Unregistered user are not able to click on submit button | Pass | Mayuri A. Jadhav
TC_013 | Verify user should be redirecting to reset password page when click on submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether user should be redirecting to reset password page when click on submit button | Not Applicable | user should be redirecting to reset password page when click on submit button | user is redirecting to reset password page when click on submit button | Pass | Mayuri A. Jadhav
TC_014 | Verify that user should able to click on Back and Submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether user should able to click on Back and Submit button button | Not Applicable | user should able to click on Back and Submit button | user is able to click on Back and Submit button | Pass | Mayuri A. Jadhav
TC_015 | Verify that Back and Submit button should be highlighted | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether Back and Submit button are highlighted | Not Applicable | Back and Submit button should be highlighted | Back button are not highlighted, only Submit button is highlighted | Fail | Mayuri A. Jadhav
TC_016 | Verify that Arrow cursor should change to Hand Cursor on Back and Submit button | 1.Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Forgot Password button | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check whether Arrow cursor change to Hand Cursor on buttons | Not Applicable | Arrow cursor should change to Hand Cursor on Back and Submit button | Arrow cursor is getting changed to Hand Cursor on Back and Submit button | Pass | Mayuri A. Jadhav

## Sign with OTP
Test Case ID | Test Case Description | Pre Condition | Steps to Execute | Test Data | Expected Result(ER) | Actual Result | Status | Executed QA Name
TC_001 | Verify URL of nimapinfotech is working | Open any browser | 1. Enter URL of nimapinfotech in search bar 2. Press enter | URL of nimapinfotech: https://testffc.nimapinfotech.com/ | Validate URL of nimapinfotech should be working | nimapinfotech URL is working fine and visible Login page | Pass | Mayuri A. Jadhav
TC_002 | Verify appropriate text on title bar of website | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.hover mouse pointer to title bar of webpage | Not Applicable | following message should get displayed: "Login-Test Field Force" | "Test Field Force" message is displayed | Fail | Mayuri A. Jadhav
TC_003 | Verify the design of the Login page should be displayed properly | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.Check whether design of the Login page should be displayed properly | Not Applicable | design of the Login page should be displayed properly | design of the Login page is displayed properly as expected | Pass | Mayuri A. Jadhav
TC_004 | Verify the logo of the employee attendance tracking should be visible on Login page | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.Check whether logo of the employee is visible on Login page | Not Applicable | logo of the employee attendance tracking should be visible on Login page | logo of the employee attendance tracking is visible on login page as expected | Pass | Mayuri A. Jadhav
TC_005 | Below of logo, Verify the Headline should be visible on Login page | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. Check whether Below logo Headline is visible | Not Applicable | Below logo, Headline should be visible on Login page | Below logo, Headline is visible on Login page as expected | Pass | Mayuri A. Jadhav
TC_006 | Verify that user should not able to click Sign In with OTP button with blank Email id/Mobile No. and Password field | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. user should not able to click Sign In with OTP button with blank Email id/Mobile No. and Password field | Not Applicable | user should not able to click Sign In with OTP button with blank Email id/Mobile No. and Password field | User is not able to click Sign In with OTP button with blank fields.Error message shown. | Pass | Mayuri A. Jadhav
TC_007 | Verify in textbox placeholder should be present | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check placeholder are present in textbox | Not Applicable | placeholder should be present in textbox | As expected placeholder is present in textbox | Pass | Mayuri A. Jadhav
TC_008 | Verify user should able to fill the fields | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user fill the fields | Email Id-sanu@gmail.com Password-sanurane | user should able to fill the fields | user is able to fill the fields | Pass | Mayuri A. Jadhav
TC_009 | Verify in Email Id/Mobile No field 10 digit number should be allowed | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether in Email Id/Mobile No field 10 digit number should be allowed | Mobile No-4857485965 | Email Id/Mobile No field 10 digit number should be allowed | Email Id/Mobile No field minimum 10 digit are allowed and if mobile no exist,user is able login | Pass | Mayuri A. Jadhav
TC_010 | Verify user should not able to click on Sign In with OTP button with invalid email id | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should not able to click on Sign In with OTP button with invalid email id | Email Id- abcgmail, fhg@, cvcb@gmail, wed@gmail. | user should not able to click on Sign In with OTP button with invalid email id | As expected user is not able to click Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_011 | Verify only registered Email Id/Mobile, users should be able to click Sign In with OTP button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check whether only registered Email Id/Mobile, users should be able to click on Sign In with OTP button | Email Id-sanu@gmail.com Mobile No-4857485965 | only registered Email Id/Mobile, users should be able to click on Sign In with OTP button | As expected only registered Email Id/Mobile, user is able to click on Sign In with OTP button.Unregistered user are not able to click on Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_012 | Verify user should be able to see the password by clicking on eye icon | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check whether user should be able to see the password by clicking on eye icon | Not Applicable | user should be able to see the password by clicking on eye icon | user is able to see the password by clicking on eye icon | Pass | Mayuri A. Jadhav
TC_013 | Verify that user should able to click on Forgot password, Sign In and Sign In with OTP button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should able to click on Forgot password, Sign In and Sign In with OTP button | Not Applicable | user should able to click on Forgot password, Sign In and Sign In with OTP button | user is able to click on Forgot password, Sign In and Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_014 | Verify that Forgot password, Sign In and Sign In with OTP button should be highlighted | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether Forgot password, Sign In and Sign In with OTP button are highlighted | Not Applicable | Forgot password, Sign In and Sign In with OTP button should be highlighted | Forgot password is not highlighted, only Sign In and Sign In with OTP button are highlighted | Fail | Mayuri A. Jadhav
TC_015 | Verify that Arrow cursor should change to Hand Cursor on Forgot password, Sign In and Sign In with OTP button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether Arrow cursor change to Hand Cursor on buttons | Not Applicable | Arrow cursor should change to Hand Cursor on Forgot password, Sign In and Sign In with OTP button | Arrow cursor is getting changed to Hand Cursor on Forgot password, Sign In and Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_016 | Verify user should be redirecting to login-with-otp page when click on Sign In with OTP button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should be redirecting to login-with-otp page when click on Sign In with OTP button | Not Applicable | user should be redirecting to login-with-otp page when click on Sign In with OTP button | user is redirecting to login-with-otp page when click on Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_017 | Verify user should get OTP on register email id/mobile no. | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should get OTP on register email id/mobile no | Not Applicable | user should get OTP on register email id/mobile no. | register user is getting OTP on email id/mobile no. | Pass | Mayuri A. Jadhav
TC_018 | Verify if user click on here resend hyperlink, user should get OTP on register email id/mobile no | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user click on here resend hyperlink, user should get OTP on register email id/mobile no | Not Applicable | user click on here resend hyperlink, user should get OTP on register email id/mobile no | user click on here resend hyperlink, user is getting OTP on register email id/mobile no | Pass | Mayuri A. Jadhav
TC_019 | Verify user should be redirecting to application dashboard when click on submit button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should be redirecting to application dashboard when click on submit button | Not Applicable | user should be redirecting to application dashboard when click on submit button | As expected user is redirecting to application dashboard when click on submit button | Pass | Mayuri A. Jadhav
TC_020 | Verify when user click on Back button, user is redirecting to login page | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether when user click on Back button, user is redirecting to login page | Not Applicable | when user click on Back button, user is redirecting to login page | As expected when user click on Back button, user is redirecting to login page | Pass | Mayuri A. Jadhav

## Login
Test Case ID | Test Case Description | Pre Condition | Steps to Execute | Test Data | Expected Result(ER) | Actual Result | Status | Executed QA Name
TC_001 | Verify URL of nimapinfotech is working | Open any browser | 1. Enter URL of nimapinfotech in search bar 2. Press enter | URL of nimapinfotech: https://testffc.nimapinfotech.com/ | Validate URL of nimapinfotech should be working | nimapinfotech URL is working fine and visible Login page | Pass | Mayuri A. Jadhav
TC_002 | Verify appropriate text on title bar of website | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.hover mouse pointer to title bar of webpage | Not Applicable | following message should get displayed: "Login-Test Field Force" | "Test Field Force" message is displayed | Fail | Mayuri A. Jadhav
TC_003 | Verify the design of the Login page should be displayed properly | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.Check whether design of the Login page should be displayed properly | Not Applicable | design of the Login page should be displayed properly | design of the Login page is displayed properly as expected | Pass | Mayuri A. Jadhav
TC_004 | Verify the logo of the employee attendance tracking should be visible on Login page | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.Check whether logo of the employee is visible on Login page | Not Applicable | logo of the employee attendance tracking should be visible on Login page | logo of the employee attendance tracking is visible on login page as expected | Pass | Mayuri A. Jadhav
TC_005 | Below of logo, Verify the Headline should be visible on Login page | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. Check whether Below logo Headline is visible | Not Applicable | Below logo, Headline should be visible on Login page | Below logo, Headline is visible on Login page as expected | Pass | Mayuri A. Jadhav
TC_006 | Verify that user should not able to click Sign In button with blank Email id/Mobile No. and Password field | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. user should not able to click Sign In button with blank Email id/Mobile No. and Password field | Not Applicable | user should not able to click Sign In button with blank Email id/Mobile No. and Password field | User is not able to click Sign In button with blank fields.Error message shown. | Pass | Mayuri A. Jadhav
TC_007 | Verify in textbox placeholder should be present | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check placeholder are present in textbox | Not Applicable | placeholder should be present in textbox | As expected placeholder is present in textbox | Pass | Mayuri A. Jadhav
TC_008 | Verify user should able to fill the fields | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user fill the fields | Email Id-sanu@gmail.com Password-sanurane | user should able to fill the fields | user is able to fill the fields | Pass | Mayuri A. Jadhav
TC_009 | Verify in Email Id/Mobile No field 10 digit number should be allowed | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether in Email Id/Mobile No field 10 digit number should be allowed | Mobile No-4857485965 | Email Id/Mobile No field 10 digit number should be allowed | Email Id/Mobile No field minimum 10 digit are allowed and if mobile no exist,user is able login | Pass | Mayuri A. Jadhav
TC_010 | Verify user should not able to click on Sign In button with invalid email id | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should not able to click on Sign In button with invalid email id | Email Id- abcgmail, fhg@, cvcb@gmail, wed@gmail. | user should not able to click on Sign In button with invalid email id | As expected user is not able to click Sign In button | Pass | Mayuri A. Jadhav
TC_011 | Verify only registered Email Id/Mobile, users should be able to click Sign In button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check whether only registered Email Id/Mobile, users should be able to click on Sign In button | Email Id-sanu@gmail.com Mobile No-4857485965 | only registered Email Id/Mobile, users should be able to click on Sign In button | As expected only registered Email Id/Mobile, user is able to click on Sign In button.Unregistered user are not able to click on Sign In button | Pass | Mayuri A. Jadhav
TC_012 | Verify user should be able to see the password by clicking on eye icon | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2. check whether user should be able to see the password by clicking on eye icon | Not Applicable | user should be able to see the password by clicking on eye icon | user is able to see the password by clicking on eye icon | Pass | Mayuri A. Jadhav
TC_013 | Verify that user should able to click all buttons on login page(Forgot password, Sign In and Sign In with OTP) | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should able to click all buttons on login page(Forgot password, Sign In and Sign In with OTP) | Not Applicable | user should able to click all buttons on login page(Forgot password, Sign In and Sign In with OTP) | user is able to click all buttons on login page(Forgot password, Sign In and Sign In with OTP) | Pass | Mayuri A. Jadhav
TC_014 | Verify that all buttons on the page should be highlighted | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether all buttons on the page should be highlighted | Not Applicable | all buttons on the page should be highlighted | Forgot password is not highlighted, only Sign In and Sign In, Sign up with OTP button are highlighted | Fail | Mayuri A. Jadhav
TC_015 | Verify that Arrow cursor should change to Hand Cursor on Forgot password, Sign In, Sign up and Sign In with OTP button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether Arrow cursor should change to Hand Cursor on Forgot password, Sign In, Sign up and Sign In with OTP button | Not Applicable | Arrow cursor should change to Hand Cursor on Forgot password, Sign In, Sign up and Sign In with OTP button | Arrow cursor should change to Hand Cursor on Forgot password, Sign In, Sign up and Sign In with OTP button | Pass | Mayuri A. Jadhav
TC_016 | Verify user should be redirecting to application dashboard page when click on Sign In button | Open the website(https://testffc.nimapinfotech.com/) in browser | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether user should be redirecting to application dashboard page when click on Sign In button | Not Applicable | user should be redirecting to application dashboard page when click on Sign In button | user is not redirecting to application dashboard page when click on Sign In button.Error message displayed | Fail | Mayuri A. Jadhav

## Bug Report
Defect ID | Scenario ID | Test Case ID | Description | Steps to reproduce | Expected Result | Screenshot | Enviroment | Reported By
D_001 | (TS_001) Sign Up | TC_003 | Wrong message displayed in titile bar of Sign up page | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. hover mouse pointer to title bar of webpage | following message should get displayed: "Register-Test Field Force" | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_002 | (TS_001) Sign Up | TC_011 | In Name field numbers and special characters are allowed | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and click on submit button | In Name field numbers and special characters should not be allowed.Highlighted error message should be shown numbers and special characters are not allowed. | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_003 | (TS_001) Sign Up | TC_012 | In Mobile No field characters and special characters are not allowed but wrong error message shown'minimum field length:6' | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and click on submit button | In Mobile No field numbers and special characters should not be allowed.Highlighted error message should be shown characters and special characters are not allowed. | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_004 | (TS_001) Sign Up | TC_013 | In Mobile No field minimum 6 digit are allowed | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and click on submit button | In Mobile No field minimum 10 digit should be allowed | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_005 | (TS_001) Sign Up | TC_016 | user is able to submit register form with already used email id. | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and click on submit button | user should not able to submit register form with already used email id. | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_006 | (TS_001) Sign Up | TC_018 | selecting country other than India Mobile No field is not marked star | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and check | When user selecting country other than India all fields should be marked star | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_007 | (TS_001) Sign Up | TC_020 | When user click on submit button, User is not getting successful message and user is redirected to reset password page | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. Fill up details and click on submit button | user should be get successful message after submitting register form | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_008 | (TS_001) Sign Up | TC_022 | Forgot password, Back are not highlighted, only Submit button is highlighted | 1. Open the website(https://testffc.nimapinfotech.com/) in browser 2. click on Sign Up button 3. check all buttons are highlighted | Forgot password, Back and Submit button should be highlighted | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_009 | (TS_002) forgot Password | TC_003 | Wrong message displayed in titile bar of Forgot Password page | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.hover mouse pointer to title bar of webpage | following message should get displayed: "Forgot Password-Test Field Force" | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_010 | (TS_002) forgot Password | TC_015 | Back button are not highlighted, only Submit button is highlighted | 1.Open the website(https://testffc.nimapinfotech.com/) 2. click on Forgot Password button 3.check all buttons are highlighted | Back and Submit button should be highlighted | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_011 | (TS_003) Sign with OTP | TC_002 | Wrong message displayed in titile bar of Sign in page | 1.Open the website(https://testffc.nimapinfotech.com/) 2.click on Sign in button 3.hover mouse pointer to title bar of webpage | following message should get displayed: "Login-Test Field Force" | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_012 | (TS_003) Sign with OTP | TC_014 | Forgot password is not highlighted, only Sign In and Sign In with OTP button are highlighted | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether Forgot password, Sign In and Sign In with OTP button are highlighted | Forgot password, Sign In and Sign In with OTP button should be highlighted | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_013 | (TS_004) Login | TC_002 | Wrong message displayed in titile bar of Sign in page | 1.Open the website(https://testffc.nimapinfotech.com/) 2.click on Sign in button 3.hover mouse pointer to title bar of webpage | following message should get displayed: "Login-Test Field Force" | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_014 | (TS_004) Login | TC_014 | Forgot password is not highlighted, only Sign In and Sign In, Sign up with OTP button are highlighted | 1.Open the website(https://testffc.nimapinfotech.com/) 2.check whether all buttons are highlighted | all buttons on the page should be highlighted | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav
D_015 | (TS_004) Login | TC_016 | user is not redirecting to application dashboard page when click on Sign In button.Error message displayed | 1.Open the website(https://testffc.nimapinfotech.com/) 2.click on Sign In button | user should be redirecting to application dashboard page when click on Sign In button | Not Attached | Platform : Windows 10 Browser : Google Chrome Device : Laptop Network : Mobile Internet | Mayuri A. Jadhav